PROKON ERP

Government e-Invoicing Integration

& One-Click Tally Accounting Export

Project Proposal · Problem, Solution, End-to-End Design & Rollout Plan

| Document | Proposal for Management Approval |
| --- | --- |
| Version | 2.0 — route revised to GSP-mediated e-invoicing after total-cost review |
| Date | 25 August 2026 |
| Prepared by | Jai — Product / Engineering |
| Systems covered | Prokon ERP (invoicing) · Authorised GSP partner (e-invoice bridge) · Tally ERP 9 (accountant) |

Confidential — internal circulation only. Contains business and compliance information.

Contents

1. Executive Summary

2. Background — Where We Stand Today

3. Problem Statement

4. Proposed Solution

5. How the Complete System Works — End to End

6. Technology & Tools We Will Use

7. Accounts, Logins & Registrations Needed

8. Security & Data Safety

9. Compliance Rules Built Into the System

10. Implementation Plan & Timeline

11. Cost Analysis — Three Routes Compared Honestly

12. Risks & Mitigations

13. Design Review & Decision Log

14. Success Criteria

15. Appendix — Plain-English Glossary

1. Executive Summary

Two gaps currently exist between how we bill and how we stay compliant and keep our books:

- (A) Compliance: With turnover above ₹5 crore, GST law requires every B2B tax invoice to be registered on the government e-Invoice system (an "IRN") before it counts as a legally issued invoice. Today our ERP can only generate a placeholder — no real IRN exists.

- (B) Accounting: Our accountant maintains the books in Tally ERP 9. Every invoice we raise must be re-typed into Tally — duplicated effort, avoidable errors, and month-end delays.

This proposal covers both gaps in one project: one-click IRN generation through an authorised GSP partner — a government-licensed bridge between our ERP and the tax authority — plus a one-click export that imports straight into the accountant's Tally. Both workstreams run inside Prokon ERP using infrastructure we already pay for.

| At a glance |  |
| --- | --- |
| Recurring cost | ≈ ₹8,000–₹20,000 / year GSP subscription (volume-based; typical SME plans sit at the lower end) |
| New infrastructure to buy or maintain | None — no servers, no IP registrations, no security-certification projects |
| Build time | ~2–3 weeks (details in §10) |
| Legal status | Mandatory for us — non-compliance risks penalties of ₹10,000+ per invoice and blocked customer payments |
| Risk posture | Lowest of all available routes — the GSP carries uptime SLAs, security certifications, multi-portal failover, and keeps up with government spec changes on our behalf |

Why not the nominally “free” direct-government route? Because it is only free of licence fees — not of engineering weeks, a dedicated server, and an uncertain ₹1.5–4 lakh certification. §11 compares all three routes with full costs counted; §13 logs how we reached this decision.

2. Background — Where We Stand Today

Prokon ERP already runs our sales workflow end to end: quotations → delivery challans → tax invoices → payment tracking. The invoicing engine was built GST-aware from day one:

| Already working in Prokon ERP today | Status |
| --- | --- |
| Automatic CGST / SGST / IGST computation per line item (same-state vs inter-state) | ✅ Live |
| Buyer/seller GSTIN, place of supply, HSN codes, discount handling | ✅ Live |
| Invoice PDF generation with QR support and amount-in-words | ✅ Live |
| e-Invoice fields in database (IRN, acknowledgement no., QR payload) | ✅ Ready — unused |
| "Generate IRN" button on invoices | ⚠️ Placeholder only — creates a dummy number, not a real government IRN |
| e-Way Bill form on invoices | ⚠️ Placeholder only — records data, does not talk to any government portal |
| Tally integration | ❌ None — accountant re-types everything |

In short: the hard foundation is built. What is missing is the final mile — connecting our invoices to the government registry, and to the accountant's books.

3. Problem Statement

3.1 The compliance problem — this is now a legal requirement

Businesses with aggregate turnover above ₹5 crore are legally required to issue e-Invoices: every B2B tax invoice must be reported to an Invoice Registration Portal (IRP) run under GSTN, which validates it and returns a unique 64-character Invoice Reference Number (IRN) plus a cryptographically signed QR code that must be printed on the invoice.

If we issue a B2B invoice without a valid IRN and signed QR:

- It is treated in law as "failure to issue an invoice" (Rule 48(5), CGST Rules) — penalty ₹10,000 or the tax amount involved, whichever is higher, per invoice.

- Our customers cannot claim their input tax credit smoothly — large buyers simply stop paying until a compliant invoice reaches them.

- Manual upload through the web portal does not scale and invites typing mistakes that the portal rejects.

3.2 The accounting problem — double work every month

Our accountant keeps the statutory books in Tally ERP 9. Today, every invoice, receipt and customer change made in Prokon ERP is re-entered manually into Tally. Consequences:

- Wasted hours every month on pure data entry.

- Typing errors create mismatches between what we billed and what the books show.

- Books lag reality by days, delaying reconciliations and filings.

- No automatic audit trail linking an ERP invoice to its Tally voucher.

Bottom line: we need our invoicing to speak directly to (a) the government e-invoice registry and (b) our accountant's Tally — automatically, accurately, and with predictable costs.

4. Proposed Solution

Two workstreams, delivered together inside Prokon ERP:

Workstream A — One-click IRN generation via an authorised GSP partner

A GSP (GST Suvidha Provider) is a company licensed by GSTN to carry invoice traffic between businesses and the government's systems. They operate the certified connections, the encryption, the government-mandated security registrations, and absorb every specification change the tax authority issues. Well-known names include ClearTax, IRIS, Cygnet, EY and MasterGST.

We integrate Prokon ERP with one carefully chosen GSP: our server sends a standard invoice payload over a simple authenticated API; the GSP delivers it to the government and returns the IRN, acknowledgement and signed QR code. Once live, every B2B invoice gets, with one click (or automatically on issue):

- An IRN registered with the government against our GSTIN

- The official signed QR code printed on the PDF, verifiable by any buyer

- Acknowledgement number & date recorded for audit

- Optionally an e-Way Bill generated through the same partner for goods movement > ₹50,000

What we deliberately do NOT build (and who carries it instead):

| Obligation | Direct-route reality | With a GSP |
| --- | --- | --- |
| Government-mandated cryptography (encryption, signing, session keys) | We implement and maintain it ourselves | GSP's platform — we send plain JSON over TLS |
| Static Indian IP registration with NIC firewalls | Needs a dedicated always-on server (~₹500–800/month) just to hold a fixed address | GSP's registered infrastructure |
| Security certification (CERT-In audit risk, ₹1.5–4 L if demanded) | Our bill, our project delay | GSP's existing certification covers the pipe |
| Keeping up with government spec & endpoint changes | Our permanent maintenance duty | GSP's contractual duty — invisible to us |

How we will pick the partner (selection checklist):

- GSTN-authorised GSP status (verified against the official GSTN partner list)

- Transparent pricing — flat monthly slab vs per-IRN charges; e-Way Bill included or bundled cheaply

- Quality of developer documentation and a usable sandbox for testing

- Demonstrated uptime during month-end filing rush; responsive human support

- Data-portability commitment — our invoice data remains ours, exportable, no lock-in

Workstream B — One-click Tally export (unchanged; independent of the IRN route)

A new screen in Prokon ERP generates Tally-native XML files that the accountant imports directly into Tally ERP 9 (Gateway of Tally → Import Data). No re-typing, no mapping tools, nothing extra for them to buy:

- Two-stage files: a Masters file first (customers with GSTINs, sales ledgers split by GST rate, CGST/SGST/IGST and round-off ledgers — imported whenever new masters exist), then the Vouchers file (sales + receipts) that consumes them safely

- Deterministic unique IDs (invoice UUID + financial year + document type) embedded in every voucher — re-importing a file can never create duplicates

- Canonical ledger names exported verbatim from a controlled registry — casing or space differences can never spawn duplicate ledgers in Tally

- Pre-flight check — flags missing GSTINs, missing HSN codes, duplicate numbers and ledger-name conflicts before the file ever reaches the accountant

5. How the Complete System Works — End to End

5.1 The e-invoice journey of one invoice

SALES TEAM           PROKON SERVER           GSP PARTNER               GOVERNMENT (NIC IRP)

──────────           ─────────────           ───────────               ────────────────────

1. Create invoice

in Prokon ERP

│

2. Click

"Generate IRN" ──► 3. Build standard JSON

4. Validate master data │

│  (GSTIN, HSN, PIN…)   │

5. Send over simple ───► 6. Encrypt + sign ──────► 7. Validate invoice

authenticated API        manages tokens          & register IRN

& govt endpoints   ◄── 8. Return: IRN, Ack,

◄── plain JSON result ─────┘ (auto-retries too)      Signed QR code

9. Save to invoice record

10. Stamp PDF: QR + IRN + Ack ◄─ customer receives a fully

compliant e-invoice

Every heavy-lifting step (6–8) belongs to the licensed partner. Our engineering stays on steps 3–5 and 9–10 — the parts that know our business.

5.2 Step by step

| Step | What happens | Who/what does it |
| --- | --- | --- |
| 1 | Invoice is created as usual — nothing changes for the sales team's daily workflow | Sales team, Prokon ERP |
| 2 | "Generate IRN" clicked (or triggered automatically when invoice is issued) | User / automation |
| 3 | Server converts the invoice into the government's standard JSON schema (≈130 fields, we fill all mandatory ones) | Prokon Edge Function |
| 4 | Master-data validation: GSTIN formats, HSN length, pin codes, quantity units, invoice-number format — bad data is caught here, not rejected hours later | Prokon validator |
| 5 | Server calls the GSP's authenticated API (client-ID/secret from our secret vault) | Prokon Edge Function |
| 6–8 | GSP encrypts and signs per government mandate, submits to the IRP, auto-retries transient failures, and returns IRN + acknowledgement + signed QR | Licensed GSP platform |
| 9–10 | ERP saves everything, stamps the PDF with the official QR, IRN and acknowledgement details | Prokon ERP + PDF engine |

5.3 When the pipeline is slow or down (retry queue + legal-safe fallback)

No integration is immune to bad days — ours or the partner's. And because an issued B2B invoice legally requires an IRN (Rule 48(5)), the fallback is designed to keep business moving without ever dispatching a non-compliant tax invoice:

- If no IRN comes back, the invoice is marked “Pending IRN” and cannot be marked issued/sent while it stays pending.

- Any printout during this window carries a bold “PROFORMA — NOT A TAX INVOICE” watermark, so an invalid document can never reach a customer by accident.

- Automatic background retries with increasing waits (exponential backoff) continue for days; aging alerts escalate at day 7 and day 21.

- Manual fallback SOP: the ERP exports the government’s standard portal-upload JSON, so staff can register invoices directly on the public web portal — dispatch never stops legally, even in a prolonged outage.

- Every attempt and response is logged permanently for audit.

5.4 Cancelling an e-invoice

Law allows cancelling an IRN only within 24 hours of generation, entirely (no partial edits), and only if no e-way bill exists against it. The system enforces all three conditions and offers guided cancellation with the mandated reason codes. After 24 hours, corrections happen the standard way: a credit note against the original, which itself gets its own IRN.

5.5 The month-end Tally routine (after go-live)

ACCOUNTS PERSON (ERP)                    ACCOUNTANT (TALLY ERP 9)

─────────────────────                    ────────────────────────

1. Open Sales → Accounting Export

2. Pick date range (e.g. August)

3. Read pre-flight report — fix anything flagged

4. Download:

• Tally_Masters_Aug.xml (only if new customers/ledgers exist)

• Tally_Vouchers_Aug.xml            5. Gateway of Tally → Import Data

• Excel summary for review             • Import Masters FIRST (creates any

│                                     missing ledgers, exactly once),

│                                   • then import the Vouchers file

└── email / share files ───────►  6. Done — books now match the ERP

Safety 1: each voucher carries a deterministic unique ID (invoice UUID +

financial year + document type), so re-importing can never duplicate.

Safety 2: ledger names come verbatim from a controlled registry — casing or

space differences can never spawn duplicate ledgers in Tally.

6. Technology & Tools We Will Use

Everything below is either already part of Prokon ERP, or a licensed service chosen in Phase 0:

| Component | What we use | Why |
| --- | --- | --- |
| Frontend (screens & buttons) | Existing Prokon ERP React app — extend invoice page, settings, new export screen | No new product to learn; same UI |
| Database | Existing Supabase PostgreSQL — columns/tables for IRN storage, audit log, token cache | Already hosted, backed up, access-controlled |
| Secure server jobs | Supabase Edge Functions calling the GSP's plain authenticated REST API (credentials held in server-side secrets) | API calls and secrets cannot live in a browser. All endpoint URLs stay as configuration, so swapping provider or route later is a settings change, not surgery |
| Government bridge | Authorised GSP partner platform (chosen in Phase 0 against the §4 checklist) | Carries the certified connection: government-grade encryption/signing, token management, IP & security registrations, spec updates, multi-portal failover — all contractual duties of theirs, not projects of ours |
| Invoice PDF stamping | Existing jsPDF + QR-code libraries | Already renders our PDFs; just adds the official QR |
| Tally integration format | Tally ERP 9 native XML import (ENVELOPE / masters-first / voucher structure) | Built into Tally — accountant needs zero new tools |
| Testing | Automated unit tests covering tax maths ↔ payload ↔ Tally XML correctness | Same test framework already used by the project |

7. Accounts, Logins & Registrations Needed

This is the complete list — noticeably shorter than the direct-government alternative, because IP registrations and security-certification paperwork sit with the GSP. Nothing here requires capital expenditure beyond the subscription itself.

7.1 Registrations to complete (the homework)

| # | Account / Registration | Where | Who does it | Purpose |
| --- | --- | --- | --- | --- |
| 1 | Choose and subscribe to a GSP partner | Provider's website / sales | Director — commercial decision | Sign the plan (monthly slab preferred). Use the §4 selection checklist |
| 2 | e-Invoice portal taxpayer registration + MFA | einvoice1.gst.gov.in | Director / GST owner (needs GST portal access) | Enable our GSTIN for e-invoicing. MFA is mandatory since April 2026 — free OTP setup |
| 3 | Opt the chosen GSP on the portal + create API username/password | einvoice1.gst.gov.in | Director creates once, hands to developer privately | Authorises the partner to submit on our behalf; machine login used by our server, never seen in day-to-day use |
| 4 | Sandbox testing with GSP keys | Partner's test environment | Developer | Validate the full flow safely before switching on production |
| 5 | e-Way Bill activation (optional, Phase 5) | Same GSP partner | Director / logistics | Generate real e-way bills from IRNs through the existing subscription |

Deliberately absent from this list: static-IP registration with NIC firewalls, a dedicated gateway server, and CERT-In security-certification paperwork — under the GSP model those obligations belong to the partner, not to us.

7.2 Where the sensitive logins live

| Credential | Stored in | Who can see it |
| --- | --- | --- |
| GSP client-ID / secret + portal API username/password | Supabase Edge Function secrets (server-side environment vault) | Nobody in day-to-day operations; only server code uses them |
| Session tokens (auto-refreshed) | Locked database table — blocked from normal app users by row-level security | Server code only |
| ERP logins | Existing Prokon ERP authentication | As today |
| Tally | Accountant's own existing Tally licence/login | Accountant — unchanged |

Practical meaning: after setup, no human ever logs into a government portal for routine invoicing. Staff click one button inside Prokon ERP; our server and the GSP handle everything behind the scenes.

8. Security & Data Safety

- Secrets never touch the browser or ordinary database queries. All API credentials sit in an encrypted server-side vault; application users physically cannot read them.

- Honest data-flow note: under the GSP model, invoice payloads transit the partner's certified platform before reaching the government — unlike a fully direct pipe. This is the standard arrangement for lakhs of Indian businesses. It is governed by the partner contract and their GSTN authorisation, and mitigated by our data-portability requirement in the §4 checklist.

- Complete audit trail. Every request and response is stored locally with timestamps — instant answers during any departmental query or buyer dispute, independent of the partner.

- Tamper-proof invoices. The signed QR is applied cryptographically by the government's own IRP regardless of route; any buyer can verify authenticity.

- Least-privilege database. Token/log tables are locked by row-level security so only server code can access them.

- No lock-in. Because the connector is abstracted, changing GSP — or moving to direct integration someday — is a configuration change plus one adapter, never a rebuild. We also hold every payload and response locally, so history survives any vendor exit.

9. Compliance Rules Built Into the System

These apply identically whichever pipe carries the invoice — they are enforced by Prokon ERP itself:

| Rule (law) | How the system enforces it |
| --- | --- |
| Every B2B invoice needs an IRN + signed QR before use | One-click/auto IRN generation. While pending: bold PROFORMA watermark on any printout, and the invoice cannot be marked issued/sent (§5.3). Manual portal-upload SOP guarantees a legal route even during outages |
| Invoices must be unique regardless of letter case — IRP uppercases all numbers and treats inv-001 = INV-001 (since June 2025) | ERP forces uppercase, restricted-character invoice numbering at creation, so duplicates are impossible before they reach anyone |
| IRN cancellation only within 24 hours, only if no e-way bill exists | Cancel button appears only while legal; reason codes captured as mandated |
| Invoices older than 30 days may be rejected — applies at ₹10 Cr+ turnover today, threshold expected to move downward | Configurable hard block on backdated invoicing once we cross ₹10 Cr AATO (alert-only until then); pending queue escalates at day 7 and day 21, far before any limit |
| Master data quality (valid GSTIN, HSN codes, units) | Validation before submission — bad data stops at our door with a clear message, not a cryptic rejection |
| Books must reconcile with returns | Tally export carries the exact figures filed in GSTR-1; monthly IRN register export included for the accountant |

10. Implementation Plan & Timeline

| Phase | Scope | Duration | Depends on |
| --- | --- | --- | --- |
| 0 — Partner & portals (parallel) | Pick GSP against the §4 checklist and subscribe; portal registration + MFA; opt the GSP and generate API credentials (§7.1) | ~2–4 working days elapsed | Director decision |
| 1 — Foundation | Database migration; e-invoice payload builder + validator; automated tests | Week 1 | — |
| 2 — Partner connectivity | Wire the GSP adapter: send payloads to their sandbox, handle success/error/retry responses; endpoint URLs as configuration | Days (not weeks — no government crypto or firewall work exists on our side anymore) | Phase 0 keys |
| 3 — User experience | Invoice page wiring, error display, retry queue with PROFORMA watermark & issue-block, dashboard aging alerts, PDF with official QR, uppercase invoice numbering | Week 2 | Phase 2 |
| 4 — Tally export (parallel) | Two-stage XML generator (masters-first + vouchers), deterministic unique IDs, canonical ledger registry, export screen with pre-flight report incl. duplicate-ledger detection, accountant's how-to guide | Weeks 2–3 | Accountant confirms accounting-only vs inventory mode |
| 5 — Go live | Switch GSP key from sandbox to production → pilot on a handful of real invoices (cancel-safe within 24h) → full rollout; optional e-Way Bill activation | Week 3+ | Production activation on the partner account |

Realistic total: ~2–3 weeks — roughly half the earlier direct-integration estimate, because Phase 2 collapsed from building-and-certifying government cryptography to consuming a well-documented commercial API. The longest lead item is simply choosing the partner.

11. Cost Analysis — Three Routes Compared Honestly

Earlier drafts compared only licence fees, which flattered the “free” direct route. The table below counts everything: subscriptions, infrastructure, engineering time, and one-time risks.

| Route | Year-1 cash cost | Ongoing engineering burden | One-time / hidden risks |
| --- | --- | --- | --- |
| ★ GSP partner (recommended) | ₹8,000–₹20,000 subscription (plan-dependent) | Minimal — days per year at most | Price rises at renewal (mitigated: multi-year quote negotiated now + swappable connector); no audit exposure, no infrastructure |
| Direct NIC integration | Gateway server ₹6,000–₹9,600/yr + several engineering-weeks valued well above the subscription saved | Permanent — crypto upkeep, spec changes, endpoint migrations, firewall renewals are ours forever | CERT-In certification uncertainty: ₹1.5–4 L if demanded, plus schedule risk. Only becomes attractive at very high volumes (order of 40,000+ invoices/year) sustained over multiple years |
| Zero-spend manual stopgap | ₹0 — NIC's free offline tool (Excel → JSON → portal upload) | None to build, but someone performs manual batches weekly, forever | Human error rates, no automation, defeats the project's core purpose. Acceptable only as a temporary bridge or emergency SOP (already built into §5.3) |

Reading the numbers plainly: going direct saves perhaps ₹8,000–₹14,000 of subscription a year after its own server bill — and one demanded certification would erase a decade of that saving, before counting engineering weeks. That is why the recommendation is GSP-first, with the direct route kept alive on paper (the connector abstraction) should volumes ever justify revisiting. Hosting for our own components remains absorbed by the existing Supabase plan.

12. Risks & Mitigations

| Risk | Reality | Mitigation built in |
| --- | --- | --- |
| Pipeline downtime / slowness (ours or partner's) | Any integration has bad days; partners counteract with multi-IRP failover and SLAs, but no one is perfect | Retry queue with backoff; PROFORMA watermark + issue-block keeps dispatch legally safe (§5.3); manual portal-upload SOP; aging alerts day 7/21 |
| GSP price increase or poor service at renewal | Commercial reality of subscriptions | Multi-year pricing locked at signature where possible; connector abstraction means switching partner (or route) is configuration + one adapter — days, not months; we retain all data locally regardless |
| Invoice data transits a third party | True under any GSP model — the trade-off accepted for cost and speed | Partner must be GSTN-authorised (verified in §4 checklist); confidentiality and data-portability clauses in contract; payloads stored locally so our audit trail never depends on the vendor |
| Government changes specs / endpoints | Still happens a few times a year — but it lands on the partner now | Contractual duty of the GSP; occasional field-level updates may ripple into our payload builder, sized in days |
| Dirty master data causes rejections or duplicate Tally ledgers | #1 cause of failed submissions industry-wide | Pre-flight validation in ERP; canonical ledger registry with exact-name matching and duplicate detection in the Tally export report |
| Onboarding delays | Far smaller than the direct route — no IP whitelisting queue, no certification cycle | Phase 0 is days; all build phases proceed in parallel |
| Key-person risk on the new code | — | Fully documented (this document + technical docs + automated tests as living specification) |

13. Design Review & Decision Log

This proposal survived two independent challenge rounds. Both are recorded here so the reasoning is auditable — including the round that changed the recommended route.

Round 1 — Feasibility review of v1.0 (direct-integration draft)

| Claim raised | Verdict after verification | What changed |
| --- | --- | --- |
| “Direct API access is blocked below ₹100 Cr turnover” | Incorrect. Stale 2020-era policy; GSTN extended direct access above ₹5 Cr from Jan 2023 | Proceeded (then) as planned; written GSTN confirmation added to checklist |
| “Production needs up to 4 whitelisted Indian static IPs; serverless can't provide them” | Correct — critical. Confirmed on NIC's official onboarding page | Fixed-IP gateway was added in v1.1… then made irrelevant by Round 2 |
| “CERT-In empanelled audit is mandatory” | Half-true. Certain for the e-way-bill API; absent from the official e-invoice checklist | Treated as tail-risk — became a decisive input in Round 2 |
| “Dispatching 'Pending IRN' invoices violates Rule 48(5)” | Correct. | PROFORMA watermark + issue-block + portal-upload SOP (§5.3) — retained in v2.0 |
| “Tally aborts/duplicates on missing ledgers — masters must precede vouchers” | Correct. | Two-stage XML + canonical ledger registry (§4, §5.5) — retained in v2.0 |
| “Uppercase invoice numbering enforced by IRP” / “deterministic unique IDs needed” | Both correct. | Normalisation rule (§9) and GUID scheme (§5.5) — retained in v2.0 |
| “MPLS leased line / ₹5 L recurring infra required” | Overstated. | Never budgeted |

Round 2 — Total-cost challenge of v1.1 (this revision)

| Challenge | Verdict | Consequence |
| --- | --- | --- |
| “Once developer weeks, the gateway server and the audit gamble are counted, the GSP route is cheaper and lower-risk in year 1 — the direct route only wins after 3–4+ years, at volume, with no audit trigger” | Accepted. The v1.1 comparison counted licence fees but flattered direct integration by omitting engineering time and the certification tail-risk | Workstream A switched to GSP-primary throughout this document. Timeline halved (§10), infrastructure eliminated (§6), audit risk transferred (§11–§12). Direct NIC retained as a documented future option via the connector abstraction — revisit only above roughly 40,000+ invoices/year |
| “NIC's free offline bulk-upload tool could be a zero-cost path” | Partially. Truly ₹0, but manual batches defeat the automation purpose | Kept only as the emergency SOP inside §5.3, not as the strategy |
| “Workstream B is independent of the IRN route” | Correct. | Tally export design untouched across revisions — confirming the two workstreams were correctly separated |

14. Success Criteria

- 100% of B2B invoices carry a valid government IRN and the official signed QR on the PDF

- Zero non-compliant invoices ever dispatched — watermark and issue-block enforced by the system, not by memory

- Zero manual re-entry of invoices/receipts into Tally — monthly import takes the accountant under five minutes

- Zero duplicate vouchers or ledgers in Tally, guaranteed by deterministic IDs and canonical names

- Full audit trail: any invoice traceable from creation → IRN → Tally voucher in under a minute

- Predictable spend: one annual subscription, no infrastructure, no surprise certification bills

- Swappable plumbing: changing GSP — or adopting direct integration someday — achievable within about a week of work

15. Appendix — Plain-English Glossary

| Term | Meaning |
| --- | --- |
| IRN (Invoice Reference Number) | The 64-character unique ID the government assigns to each e-invoice. Proof the invoice is officially registered. |
| IRP (Invoice Registration Portal) | The government system that accepts invoices and issues IRNs. NIC operates the main ones. |
| GSP (GST Suvidha Provider) | A company licensed by GSTN to carry GST/e-invoice traffic between businesses and government systems. Chosen here as our recommended route. |
| Multi-IRP failover | If one government registration portal is down, the GSP automatically submits through another approved one. |
| Signed QR code | QR code cryptographically sealed by the government; printed on the invoice so any buyer can verify authenticity. |
| e-Way Bill (EWB) | Electronic permit required for moving goods worth over ₹50,000; can be generated from an IRN. |
| GSTIN | GST Identification Number (15 characters) of a business. |
| HSN code | Standardised product classification code required on invoices. |
| Sandbox | A practice/test environment — identical behaviour, no real consequences. |
| Static IP whitelisting | Firewall practice where the government only accepts API traffic from pre-registered server addresses. Required on the direct route; handled by the GSP otherwise. |
| CERT-In security audit (SAR / VAPT) | A penetration-test report from a government-empanelled auditor. Required for some integrations; avoided entirely under the GSP route. |
| Proforma watermark | A large “NOT A TAX INVOICE” stamp printed on documents that are not yet legally issued — prevents accidental dispatch of non-compliant paperwork. |
| Tally XML | Tally's native import file format. Our export produces files Tally ingests natively — no plugins. |
| Voucher (Tally) | A bookkeeping entry in Tally — e.g., a Sales or Receipt entry. |
| Ledger masters | Tally's master lists — customers, sales accounts, tax accounts — created once, reused forever. |
| Exponential backoff | Retry pattern: try again after 1 min, then 2, then 4… avoids hammering a struggling pipeline. |
| TCO (Total Cost of Ownership) | Everything a choice really costs — licences, servers, people-time, risks — not just the sticker price. |

Recommendation: approve the GSP subscription (Phase 0, §4 checklist) and start this week. It is the only step awaiting a decision — everything else proceeds in parallel and lands in roughly three weeks.